NPFC-2022-TWG CMSA05-WP02 (Rev. 1)

TWG CMSA Work Plan, 2022-2026

The Chair and vice-Chair of the TWG CMSA revised and updated the TWG CMSA work plan up to 2026. The Work Plan has been reviewed and revised at the TWG CMSA05 meeting.

FIVE-YEAR WORK PLAN

Technical Working Group on Chub Mackerel Stock Assessment (TWG CMSA)

Priority list:

- Data preparation and review of biological information

- Develop an operating model

- Test stock assessment models (VPA, ASAP, KAFKA, SAM, state-space production model)

- Conduct stock assessment of chub mackerel

- Set biological reference points

- Provide scientific advice on the management of chub mackerel stock to the Commission

- Regularly update and refine inputs

| ITEM | 2022 spring | 2022 autumn | 2023 1st half | 2023 2nd half | 2024 | 2025 | 2026 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |  |  |
| Research survey indices | Review the data used for the stock assessment | Review (Finalize) the data used for the stock assessment | Finalize the data used for the stock assessment | Update | Update | Update | Update |
| CPUE indices | Review standardized CPUE indices for stock assessment | Review standardized CPUE indices for stock assessment | Finalized CPUE standardization | Update | Update | Update | Update |
| Catch data/catch composition | Review the data used for the stock assessment | Review the data used for the stock assessment | Finalize the data used for the stock assessment | Update | Update | Update | Update |
| Biological parameters (maturity, M, weight) | - Review biological parameters - Determine the range of assumption for preliminary stock assessment | Determine the range of assumption for preliminary stock assessment | Finalize assumptions for the stock assessment | Review biological parameters | Review biological parameters | Review biological parameters | Review biological parameters |
| Operating model (OM) |  |  |  |  |  |  |  |
| Development of operating model |  |  |  |  |  |  |  |
| Testing stock assessment models | - Consultant drafts a report about the performance of the candidate stock assessment models (intersessional) - Discuss how to rank the stock assessment model candidates based on the performance measures (intersessional) | - Determine how to rank the stock assessment model candidates based on the performance measures - Choose the best SA model(s) |  |  |  |  |  |
| Stock assessment |  |  |  |  |  |  |  |
| Benchmark stock assessment | Initiate discussion about specifications of future projection methods |  | - Determine the method for future projection - Conduct preliminary stock assessment | Complete stock assessment with the selected SA model(s) | Update SA model | Update SA model |  |
| Improvement and further investigation of the selected model |  |  |  |  | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model |
| Toward development of reference points |  |  |  |  |  |  |  |
| Set biological reference points (limit and target) | - Review RPs report - List candidate reference points |  | - Review RPs report - Develop a short list of reference points - Compare robustness of reference points | Choose reference points | Review reference points |  |  |

Flowchart for the development of operating models and testing stock assessment models