## Sheet2
EXTERNAL REVIEW | [8 empty] | NPFC-2023-SSC BFME04-WP19
TABLE OF RECOMMENDATIONS | DETAILS OF THE RECOMMENDATION | PRIORITY | BFME COMMENTS | ROLE | TIMING | Priority | TIMEFRAME FOR ACTION | ROLE/TASKING | Summary of comments from SC08
Recommendation 3.1.2. That the SC (and SSC for Pacific Saury) examine in greater detail the standardization of the data and indices used in the stock assessment and in the case of Pacific saury, the size and age composition traits over time. |  | High | Not applicable to BFME data | SC | Short | High | 1-2 years | SSC BF-ME, SSC PS, TWG CMSA, SWG NFS | This recommendation applies to all stock assessments
Recommendation 3.1.5. The SC should identify and describe standardised sampling gear for deepwater stocks in both Convention Area and EEZ fisheries to generate data on relative abundance and to address data gaps. |  | High | Not applicable to BFME data (for surveys) | SC | Medium | high | 1-2 years | SSC BFME | role/tasking needs to be changed to SSC BFME
Recommendation 3.1.7. To increase the usefulness of the ''footprint'' data submitted by Members, measures of effort should be reconciled with vessel monitoring system (VMS) data, where possible. |  | Medium | Possibly applicable but low priortiy | SC | Medium | medium | 3-5 years | SC ALL
Recommendation 3.1.8. The SC and TCC should coordinate formal efforts to collect standardised data and validate bycatch of associated and dependent species. | Para. 51 & 52 of Report: This recommendation is related to ecologically related species. While outside the scope of directed fishery “management” advice, having some indication of the levels of catch of associated and dependent species, by-catch, and activities such as shark-finning, would reflect a responsible approach to fishery management. Additionally, whether or not the current indicator taxa were sufficient for determining VME. | High | Added to our workplan | SC | Short | high | 5-10 years | SC ALL subsidiary bodies
Recommendation 3.2.1. The SC should provide the Commission meeting with annual summaries of the status of the stocks and these should be made public. |  | High | Added to our workplan, information contained in species summaries | SC | Short | high priority | annually | SC ALL | This is complete
Recommendation 3.2.2. The Commission should commit to a schedule for the development of full MSE, including MPs and HCRs for all priority stocks. |  | High | Can be added to workplan in the future | SC | Short | High | 5-10 years | SC ALL
Recommendation 3.2.3. If it occurs, the SC should communicate to the Commission the reasons for lack of consensus within the SC together with an identification of research needs to bridge gaps in the scientific understanding. |  | High | Add areas where there is lack of consensus to meeting report | SC | Ongoing | High | Annually | SC ALL | This SC does this in its meeting reports
Recommendation 3.3.1. The SC should annually summarize progress taken towards each element in the Five Year Work Plan. |  | High | Clarify in the five year work plan- add column to track progress | SC | Ongoing | High | Annually | SC ALL | This is complete
Recommendation 3.4.1. That the SC develop guidelines for providing advice to the Commission that reflects standards of ‘best available science’: specifically, whether advice passes defensible tests against identified criteria for ‘best available science’ (data, statistical rigor, documentation, and peer review). |  | High | We aspire to meet this objective | SC | Medium | high | 3-5 years | SC | External experts help with SA of PS and CM
Recommendation 3.4.2. That the SC pursue independent reviews of scientific advice to a greater extent. |  | High | Can be added to workplan in the future | SC | Medium | medium | 3-5 years | ALL SC
Recommendation 3.4.3. The Commission should develop a regional observer program to contribute to addressing science demands, resolve data gaps, improve data collection on bycatch, and monitor the implementation of measures. |  | High | Already in place | SC | Short | High | 3-5 years | ALL SC
Recommendation 3.4.4. The Commission should develop a program of work to examine the feasibility of introducing electronic monitoring (EM) in the NPFC Convention Area. |  | High | Maybe needs to be directed by the Commission and possibly needing a separate working group | SC | Medium | High | 3-5 years | ALL SC | This may be more of a question for the Commission.
Recommendation 3.4.5. The Commission should endeavour to engage available expertise in science issues available to other institutions and organizations (such as PICES) and seek to foster collaboration on cooperative research projects. |  | High | Already in place, could reach out to other scientists to attend BFME (FIS committee, BIO and climate changes issues) | SC | Medium | High | Annually | ALL SC | NPFC–PICES Framework for Enhanced Scientific Collaboration in the North Pacific
Recommendation 4.1.1. That the Commission and Scientific Committee increase efforts to acquire the requisite data and conclude stock assessments for all NPFC fishery resources with particular attention to the priority stocks: North Pacific armorhead, Splendid alfonsino, Pacific saury, Chub mackerel, Blue (Spotted) mackerel, Japanese sardine, Japanese flying squid and Neon flying squid. These assessments should provide the knowledge and understanding required to adopt more enduring and scientifically validated CMMs to achieve sustainable levels of fishing mortality. |  | High | Already on our workplan, we could identify mechanisms to fill data known data gaps for bottom fish species | SC | Medium | High | 1-2 years | ALL SC
Recommendation 4.1.2. That pending the results of stock assessments and where information is lacking, the Commission adopt a precautionary approach (taking account of the risk of overfishing and whether stocks are overfished) to the setting of catch limits. |  | High | Relevant for the Commission, but with input from SSC on stock status, likely needs to be addressed on a shorter term | SC | Short | likely a shorter ter m | 3-5 years | ALL SC
Recommendation 4.2.4. That the Commission dedicate effort and resources to the collection of data relating to bycatch and species taken incidentally in all NPFC fisheries. |  | High | Already in place with observer progrma | SC | Medium | high | 3-5 years | SC ALL
Recommendation 4.2.5. That the SC and the TCC each undertake a comprehensive assessment, updated annually, summarizing the NPFC data inventories and the status of data gaps and deficiencies in NPFC data and report the outcomes to the annual session of the Commission. |  | High | Task for secretariat for NPFC data to report to subsidiary bodies ((NPFC data inventoris) Add standing agenda item where we indicate the data gaps (e.g. fishery independent survey data) and deficiencies to annual meeting | SC | Short | High | annually | SC ALL
· SC to undertake a review of the scientific aspects of the 50kg VME encounter threshold (including practices in other RFMOs) for possible revision; |  |  | Complete although with some further analysis and revisitation of these thresholds in the coming year (SWG-VME) | SC |  | high | 1-2 years | SWG VME/SSC BFME | This is partially complete
· SC to re-visit the recommendations of SC03 and SSC VME03 and provide a transparent assessment of the value of including sponges and hydrocorals as VME indicator taxa in conjunction with supporting an initiative to develop a quantitative method for the identification of VMEs; and |  |  | Included sponges, developed some quantitative definitions of VME and annually review and adjust/add to these definitons, will revisit this in coming year for hydrocorals(SWG-VME) | SC |  | med | 1-2 years | SWG VME/SSC BFME | This is partially complete: glass sponge and demosponges were added in 2023; a quantitative method for VME identification was endorsed in 2023; SWG VME could discuss adding hydrocorals to the list of VME indicator taxa